## Gantt Chart
BCD WEBSITE BUILD — GANTT CHART
Project: 01 Mar – 31 May 2026 ¦ Today: 18 Mar 2026 ¦ 9/32 Tasks Complete ¦ Overall Progress: 49% | [7 empty] | 01/03 | 08/03 | 15/03 | 22/03 | 29/03 | 05/04 | 12/04 | 19/04 | 26/04 | 03/05 | 10/05 | 17/05 | 24/05
Phase | Task Name | Start | End | Wks | % Done | % Left | Status | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13
Planning | Define Project Scope | 01 Mar | 07 Mar | 1 | 100% | 0% | Complete
| Wireframing & UX Design | 01 Mar | 14 Mar | 2 | 100% | 0% | Complete
| Brand Guidelines Setup | 01 Mar | 07 Mar | 1 | 100% | 0% | Complete
Design | Homepage Design | 08 Mar | 14 Mar | 1 | 100% | 0% | Complete
| Course Catalog Page Design | 08 Mar | 21 Mar | 2 | 100% | 0% | Complete
| Course Detail Page Design | 15 Mar | 28 Mar | 2 | 80% | 20% | In Progress
| User Dashboard Design | 15 Mar | 28 Mar | 2 | 60% | 40% | In Progress
| Mobile Responsive Design | 22 Mar | 04 Apr | 2 | 35% | 65% | In Progress
Frontend | HTML / CSS Structure | 15 Mar | 21 Mar | 1 | 100% | 0% | Complete
| Navigation & Header | 15 Mar | 21 Mar | 1 | 100% | 0% | Complete
| Homepage Build | 22 Mar | 04 Apr | 2 | 90% | 10% | In Progress
| Course Catalog Page | 29 Mar | 11 Apr | 2 | 70% | 30% | In Progress
| Course Detail Page | 05 Apr | 18 Apr | 2 | 45% | 55% | In Progress
| User Dashboard UI | 12 Apr | 25 Apr | 2 | 25% | 75% | In Progress
| Payment Integration UI | 19 Apr | 02 May | 2 | 10% | 90% | In Progress
Backend | Database Setup | 15 Mar | 21 Mar | 1 | 100% | 0% | Complete
| User Authentication | 22 Mar | 04 Apr | 2 | 100% | 0% | Complete
| Course Management System | 29 Mar | 18 Apr | 3 | 75% | 25% | In Progress
| Payment Gateway Integration | 05 Apr | 25 Apr | 3 | 55% | 45% | In Progress
| Video Streaming Integration | 12 Apr | 02 May | 3 | 30% | 70% | In Progress
| Progress Tracking System | 19 Apr | 09 May | 3 | 15% | 85% | In Progress
| Certificate Generation | 26 Apr | 09 May | 2 | 0% | 100% | Not Started
Content | Course Content Upload | 05 Apr | 25 Apr | 3 | 45% | 55% | In Progress
| Blog / Articles Section | 26 Apr | 09 May | 2 | 0% | 100% | Not Started
| SEO Optimisation | 19 Apr | 09 May | 3 | 20% | 80% | In Progress
Testing | Unit Testing | 03 May | 09 May | 1 | 0% | 100% | Not Started
| User Acceptance Testing | 03 May | 16 May | 2 | 0% | 100% | Not Started
| Performance Testing | 10 May | 16 May | 1 | 0% | 100% | Not Started
| Bug Fixes | 10 May | 23 May | 2 | 0% | 100% | Not Started
Launch | Staging Deployment | 17 May | 23 May | 1 | 0% | 100% | Not Started
| Final QA Review | 17 May | 23 May | 1 | 0% | 100% | Not Started
| Production Launch | 24 May | 30 May | 1 | 0% | 100% | Not Started
|  | Done | In Progress | Not Started | Avg % Done | Avg % Left | Overall
PROJECT SUMMARY |  | 9 | 14 | 9 | 48.59% | 51.41% | 9/32 Tasks Done
LEGEND: | ■ Complete | ■ In Progress | □ Remaining | ■ Today (W3) | ○ Not Started

## Summary Dashboard
BCD WEBSITE BUILD — PROJECT DASHBOARD
As of 18 March 2026 ¦ 9 of 32 tasks complete ¦ Overall: 49% done
Total Tasks | Completed | In Progress | Not Started | Avg % Done | Avg % Remaining
32 | 9 | 14 | 9 | 48.59% | 51.41%
Phase | Total | Done | In Progress | % Complete | Status
Planning | 3 | 3 | 0 | 100% | Complete
Design | 5 | 2 | 3 | 75% | In Progress
Frontend | 7 | 2 | 5 | 62.86% | In Progress
Backend | 7 | 2 | 4 | 53.57% | In Progress
Content | 3 | 0 | 2 | 21.67% | In Progress
Testing | 4 | 0 | 0 | 0% | Not Started
Launch | 3 | 0 | 0 | 0% | Not Started